## Start here
SEO SITE MIGRATION TEMPLATE
A redirect map and a 30-step checklist
Free from SEOSage (seosage.co). Edit it, reuse it and share it. No sign-up.
1 Crawl the live site first
Save the crawl. Paste the address list into the Redirect map sheet, one row per old address.
2 Add the numbers
From Search Console, add clicks for each old address, so you can fix the important ones first.
3 Fill in the new address
Every old address that matters needs one new address. Choose the closest match, never the home page by default.
4 Test on staging
Crawl the staging site. Mark each row Tested when the old address reaches the new one in a single step.
5 Work through the Checklist sheet
Thirty steps in three stages: before, launch day, after. Tick each as you finish it.
6 Crawl again and compare
After launch, crawl the new site and compare it with your first crawl. The Summary sheet counts your progress.
The two example rows in the Redirect map are made up. Delete them before you start.

## Redirect map
Old address | New address | Redirect type | Priority | Clicks (old page) | Tested? | Final status | Hops | Notes
https://example.com/old-blog/seo-tips/ | https://example.com/blog/seo-tips/ | 301 | High | 120 | Yes | 200 | 1 | Example row (made up): moved folder.
https://example.com/shop/cat?id=14 | https://example.com/shop/shoes/ | 301 | Medium | 40 | No |  |  | Example row (made up): parameter address to clean address.

## Checklist
CHECKLIST
30 steps in three stages
# | Stage | Step | How | Done?
1 | Before the migration | Set the goal and the date | Write down what changes: domain, URLs, platform or design. Agree who signs off.
2 | Before the migration | Crawl the live site and save the crawl | This is your baseline. You will compare against it later.
3 | Before the migration | Export the pages that matter | Top pages and queries from Search Console, and top landing pages from analytics.
4 | Before the migration | Save the current sitemap, robots.txt and redirects | Keep copies, so you can check what changed.
5 | Before the migration | Build the redirect map | List every old address and the new address it should go to. Start with pages that get visits or links.
6 | Before the migration | Keep URLs the same where you can | Every changed address is a risk. Change only what you must.
7 | Before the migration | Keep titles, headings and text of important pages | Do not rewrite pages during a migration. Change one thing at a time.
8 | Before the migration | Build the staging site and keep it out of search | Use a password or a noindex tag, and note that it must be removed at launch.
9 | Before the migration | Crawl the staging site | Check titles, canonicals, internal links, status codes and language tags before launch.
10 | Before the migration | Test the redirect map on staging | Each old address should reach the right new page in one step.
11 | Before the migration | Prepare the new sitemap and robots.txt | List only live, indexable pages. Do not copy a blocking rule from staging.
12 | Before the migration | Check speed on the new templates | Test a home, category and article page on the new design.
13 | Launch day | Choose a quiet day and agree a rollback plan | Know who can undo the change, and how.
14 | Launch day | Switch the site and remove the staging block | Take off the password, the noindex tag and any robots.txt block.
15 | Launch day | Turn on the 301 redirects | Include http to https and www to non-www, or the reverse.
16 | Launch day | Submit the new sitemap in Search Console | For a domain change, also use the Change of address tool.
17 | Launch day | Crawl the live site straight away | Do not wait for Google to tell you about a problem.
18 | Launch day | Test the top 50 old addresses by hand | Each should land on the right page in one hop, with status 200 at the end.
19 | Launch day | Check robots.txt and noindex on the live site | Staging settings left on are the most expensive mistake.
20 | Launch day | Check that analytics and forms work | A migration can break tracking and contact forms.
21 | After the migration | Compare the new crawl with the baseline | Look for missing pages, new errors and changed titles. Use the compare view.
22 | After the migration | Fix 404 errors and redirect chains | Point each old address at its final destination in one step.
23 | After the migration | Update internal links to the new addresses | Do not rely on redirects for your own links.
24 | After the migration | Watch Search Console every week | Check the Page indexing and Performance reports for drops and new errors.
25 | After the migration | Keep old addresses out of the new sitemap | The sitemap should list only the new, live pages.
26 | After the migration | Update profiles and links you control | Social profiles, directories, email signatures and ads.
27 | After the migration | Ask important linking sites to update their links | Start with the sites that send the most visits.
28 | After the migration | Keep the redirects in place | Google advises keeping them for as long as possible, at least a year.
29 | After the migration | Crawl again every month and compare | Catch new problems early.
30 | After the migration | Review the results and write them up | Compare visits, impressions and errors with the baseline, a few weeks after launch.

## Summary
SUMMARY
Where you are
Old addresses in the map
High priority addresses
Addresses tested
Addresses with more than one hop
Checklist steps done (of 30)